Recommendations - from the evaluator’s mid term report of the ecotourism project

1. Reorientation and Stakeholder Engagement

- Reorientation Get-Together (Mid-2025)

  - Review project progress, identify gaps, and plan for the next phase.

  - Validate the new Ladakh Ecotourism Policy (November 2024).

  - Strengthen relationships with stakeholders, develop a platform for entitlements, and adopt a rights-based advocacy approach.

  - Upgrade the digital map, particularly Google Maps, to enhance visibility.

2. Women’s Empowerment and Livelihood Development

- Panamik Village Women’s Group Café & Handicraft Centre

  - Link the Women's Group to the Women’s Development Department/Scheme for entitlements and reduced lease costs.

  - Register the group with the local lead bank for loans (livestock, non-farm activities).

  - Organize a weekly cleanliness awareness program and display waste management posters (plastic, soap covers, etc.).

3. Soil and Agricultural Improvement

- Improvement of Soil Quality and Kitchen Gardens

  - Provide training in vermicomposting, organic manure, and pest repellent techniques.

  - Encourage entrepreneurship in organic inputs and soil fertility management.

  - Address pest issues in onion crops and develop an integrated pest management strategy.

4. Waste Management and Environment Protection

- Non-Biodegradable Waste Management

  - Follow up with the government regarding waste collection trucks for Achinathang and surrounding villages.

  - Establish an alternative non-biodegradable waste collection unit in the interim until government trucks are sanctioned

5. Tourism Promotion and Diversification

- Wildlife & Niche Tourism Promotion

  - Develop a marketing strategy to promote wildlife tourism for Himalayan brown bears and Ibex in Mushkoo Village.

- Organic Certification Promotion

  - Promote organic farming as a tourism attraction in certified villages like Takmachik (evaluator mentions Skampuk).

  - Focus on farm-based livelihoods to enhance food, nutrition, and ecological security.

- Culture and Craft Promotion

  - Develop similar plans for Likir village.

6. Health and Safety in Homestays

- Health and Safety Measures

  - Ensure that all homestays have first aid kits and common medicines for emergencies.

  - Install CCTV cameras in common areas for enhanced security.

7. Seed Banks and Agricultural Sustainability

- Seed Bank Development

  - Establish seed banks with traditional, cold-resistant vegetable varieties.

  - Develop a seed production and storage system to empower farmers, youth, and women.

  - Provide "train-the-trainer" programs to disseminate seed production techniques and business skills.

8. Homestay Promotion and Marketing

- Promote Homestays in Remote Villages

  - Install large, visible signboards at key locations with homestay contact details (e.g., Kargil Memorial with contact details of homestays from Bhimbat and Mushkoo villages).

  - Register homestays with the government for official recognition and support.

  - Explore Government’s Tourism Incentive Policy to secure capital subsidies for infrastructure improvement and expansion.

  - Market homestays through digital platforms (QR codes, GPS maps) and enhance visibility in remote areas.

9. Marketing, Value Addition, and Local Livelihoods

- Marketing and Value-Added Product Development

  - Promote linkages between village and urban markets for vegetables and local products.

  - Train youth to produce and market value-added products (e.g., apricot jam, juice, candies).

  - Partner with ecotourism and ethical travel platforms for global marketing.

10. Training and Capacity Building

- Training Programs for Local Stakeholders

  - Conduct training and awareness sessions on various local challenges, sustainable farming, waste management, and tourism promotion.

  - Offer digital literacy training for villagers to promote and market their services online.

  - Introduce creative local means to educate travellers (e.g., through plays, short films, etc. for traveler education).

  - Organize an exposure tour and knowledge exchange programs for LEHO’s team, including a visit to Sikkim for learning best practices in organic farming and ecotourism.

11. Infrastructure and Community Development

- Village Development and Infrastructure

  - Improve connectivity in remote areas (e.g., internet, wifi access).

  - Strengthen the Village Development Committees (VDCs) through exposure tours, networking, and capacity building.

12. Water and Irrigation Management

- Water Management and Drip Irrigation

  - Increase the project budget for water management activities, including drip irrigation, which could not be implemented due to fund constraints.

13. Monitoring and Project Management

- Monitoring and Evaluation

  - Develop a quarterly monitoring system with both qualitative and quantitative targets for key activities.

  - Establish a real-time monitoring system for income generation, homestay occupancy, vegetable production, handicraft income, and visitor statistics.

  - Utilize village coordinators and tour operators for real-time data collection.

14. Solar Dryers for Local Produce

- Distribution of Solar Dryers

  - Provide solar dryers to improve the hygienic drying of local fruits and vegetables for better shelf life and marketability.

15. Animal Fencing and Protection

- Fencing Techniques

  - Introduce fencing techniques to protect farmlands from stray animals, which often damage crops.